## How to use
AI use-case prioritization worksheet
Purpose: rank candidate AI projects so you start with the one most likely to pay off safely. One row per use case, not per tool.
Worksheet tab: overwrite the four [Example] rows. They describe a hypothetical professional-services company of about twenty people; their scores are illustrations of the method, not measurements. Text in [square brackets] is a placeholder.
Score Value, Data sensitivity, Effort and Risk from 1 to 5 using the definitions on the Scales tab. Value counts in a project's favour; data sensitivity, effort and risk count against it. Answer the five readiness checks Yes or No; Readiness is the number of Yes answers (minimum 1). Readiness, the score and the result stay blank until all five checks are answered, so a half-filled row is never ranked or gated by mistake. Score with the people who do the work, not only the people who want the project.
Score / 100: the three factors that count against a project are flipped (6 minus the score), the five factors are weighted (equal weights by default, set on the Scales tab), added, and scaled so that the worst possible row scores 0 and the best 100.
Gated? = Yes when data sensitivity or risk reaches the gate on the Scales tab (default 5), or readiness is at or below its gate (default 1). A gated row shows 'Prerequisites first' whatever its score: do the compliance or governance work before it, e.g. if you are a HIPAA covered entity or business associate, then among other things a business associate agreement with the AI vendor generally has to be in place before protected health information (PHI) is entered (45 CFR 164.502(e)); if your DoD contracts include DFARS 252.204-7012, NIST SP 800-171 applies to any contractor system that processes, stores or transmits covered defense information, including an AI tool, and a cloud AI service that stores, processes or transmits that information must meet security requirements equivalent to the FedRAMP Moderate baseline; if the AI's output becomes or changes a GxP record, whether, and how far, the tool must be validated for that use depends on a documented risk assessment of its effect on product quality, safety and record integrity; the predicate rules that require the record apply, and FDA 21 CFR Part 11 or EU GMP Annex 11 may also apply. Score its risk 5 even when the drafting looks routine; once your quality unit has made and recorded that decision, it signs off the row in 'Prerequisites signed off', and the score stays at 5. AI that informs patient care can be regulated by FDA as a medical device, and only some clinical decision support software is excluded, so get regulatory advice first. Never lower a score, or raise a gate setting, to clear the gate: regulated data stays at 5. Once the prerequisites are in place and documented, a named approver enters their name and the date in 'Prerequisites signed off' (leave it blank until then: any entry lifts the gate); that lifts the sensitivity and risk gate for the row, which is then ranked on its score. The readiness gate still applies. The approver should have authority for that area (e.g. the quality unit for GxP records, the privacy or security officer for PHI) and not be the person proposing the project. A typed name here does not meet the 21 CFR Part 11 requirements for electronic signatures and is not a validation record; keep the real approvals in your own quality or compliance system. If the tool, the data or the use changes, clear the sign-off and re-score the row. Signed-off rows that are still at the gate are shaded amber. The gate is modelled on the NIST AI RMF Playbook's suggested action for MAP 1.5: identify a maximum allowable risk tolerance above which the system will not be deployed.
Result: ungated rows scoring 70 or more = 'Do first', 50 to 69 = 'Next', under 50 = 'Later'. Rank orders the ungated rows by score (1 = highest). The thresholds are CIO Support's suggestion for a small company, not a NIST rule; change them on the Scales tab.
Then: pilot the top one or two with a person checking every output, measure against today's baseline, and decide in advance what result means expand, change or stop (NIST AI RMF MANAGE 1.1). Re-score after each pilot and at least quarterly; readiness changes as you fix gaps. Move use cases that go live into your AI risk register and AI inventory.
NIST AI 100-1 (AI RMF 1.0) does not prescribe a scoring method or risk tolerance. The factors give evidence for its MAP 1.4, MAP 3.1 and MAP 3.2 and, by analogy, MANAGE 1.2 (prioritizing treatment of documented AI risks); readiness relates to GOVERN 1.3 and MANAGE 1.1. See the NIST mapping tab. NIST says AI RMF 1.0 is being revised; check the subcategory numbers against the current version. https://nvlpubs.nist.gov/nistpubs/ai/NIST.AI.100-1.pdf
Explanation and worked example: https://cio.support/ai/which-ai-projects-should-a-small-business-do-first/
CIO Support by LAN Service Group · cio.support
Free to copy, edit and use inside your organization. General guidance, not legal advice. Not published or endorsed by NIST.

## Worksheet
ID | Candidate use case (one per row) | Team and owner | Data it needs | Value (1-5) | Data sensitivity (1-5) | Effort (1-5) | Risk (1-5) | Approved tool on company accounts? | Data in known places, permissions reviewed? | Named owner? | Policy covers this use? | Baseline measured (time or quality today)? | Prerequisites signed off (approver name and date; gated rows only) | Readiness (1-5, calculated) | Score / 100 (calculated) | Gated? (calculated) | Result (calculated) | Rank (calculated) | Why these scores | Next step
U-01 | [Example] Worked example: draft routine proposals and client emails from our own templates in the approved AI assistant; a person edits every draft | [Sales lead] | Our proposal and email templates; client names and scope (Internal) | 4 | 2 | 2 | 2 | Yes | Yes | Yes | Yes | No | [6 empty] | Value 4: several people write these every week and the time can be measured. Sensitivity 2: internal business information, no regulated data. Effort 2: tool already licensed, templates exist. Risk 2: a person edits every draft before a client sees it. Readiness 4: no baseline yet. | Time a few proposals today (baseline), then pilot with 3-4 willing users and compare.
U-02 | [Example] Website chatbot answering customer questions from published FAQs | [Marketing lead] | Published FAQs; customers may type their contact details | 3 | 2 | 3 | 3 | No | Yes | Yes | Yes | No | [6 empty] | Risk 3: answers reach customers directly. Effort 3: a new tool and configuration. Readiness 3: no approved chatbot tool or baseline yet. | Choose and approve a tool; record how many routine questions arrive today; hand orders, refunds and complaints to a person.
U-03 | [Example] Microsoft 365 Copilot summarising and finding content across all SharePoint and OneDrive files | [IT lead or MSP contact] | All SharePoint and OneDrive files, including HR files (personal data) | 3 | 4 | 3 | 3 | Yes | No | Yes | No | No | [6 empty] | Sensitivity 4: HR files with personal data are within reach. Microsoft states Copilot 'only surfaces organizational data to which individual users have at least view permissions' (https://learn.microsoft.com/en-us/microsoft-365/copilot/microsoft-365-copilot-privacy, checked by CIO Support 2026-10-20; re-read it yourself). Permissions not yet reviewed, so readiness 2. | Review sharing and permissions on sensitive sites, extend the AI policy to Copilot, then re-score.
U-04 | [Example] AI screening or ranking of job applicants | [CEO] | Applicant CVs and application data (personal data) | 3 | 4 | 3 | 5 | No | No | Yes | No | Yes | [6 empty] | Risk 5: shapes decisions about people, so the row is gated whatever its score. NIST AI 600-1 lists harmful bias or homogenization among generative AI risks. | Not a first project. Take employment-law advice and set governance and human review before any AI is used in hiring.

## Scales
Scoring scales, weights, gate and thresholds (CIO Support suggestion, not a NIST scale; edit to suit)
Score | Value (higher is better) | Data sensitivity (higher counts against) | Effort (higher counts against) | Risk (higher counts against)
1 | Rare task or nice-to-have; saves little time. | Public information only. | Runs in a tool you already license; no integration or data clean-up. | A wrong output stays internal and is easy to spot and fix, and the tool cannot show data to the wrong person.
2 | Saves some time for one person on an occasional task. | Internal business information; no personal data beyond business contact details. | Small setup: templates, prompts, short training. | A person checks every output before anyone outside the team sees it.
3 | Saves noticeable time on a weekly task for a few people, or improves quality on a regular task. | Confidential business information, such as financials, pricing, contracts or client-confidential material. | A new licence or configuration change, or a pilot that needs some data preparation. | Output reaches customers or others directly, affects money, or the tool could show confidential data to the wrong employee.
4 | Frequent task done by several people, and the time it takes today can be measured. | Personal data about customers, employees or applicants, such as HR files. | Integration with a business system, or significant data clean-up or permissions work. | Output feeds legal, contractual, financial-reporting or safety matters.
5 | Frequent, done by several people or central to serving customers, and the gain can be measured against today's time. | Regulated data: health information, including protected health information (PHI) and clinical-trial participant data; Controlled Unclassified Information (CUI); GxP records; payment card data; or data a contract restricts. | Custom build, model training or major data work. | Makes or materially shapes a decision about a person (hiring, credit, care), creates or changes a GxP record (e.g. SOP, batch record, deviation, study report), or acts without a person approving it.
Readiness is not scored by hand: it is the number of the five readiness checks answered Yes on the Worksheet (approved tool on company accounts; data in known places with permissions reviewed; named owner; policy covers this use; baseline measured), with a minimum of 1. It stays blank until all five checks are answered.
Gate: a row at or above the data sensitivity or risk gate stays 'Prerequisites first' until a named approver fills in 'Prerequisites signed off' on the Worksheet. Never lower a score to clear the gate; regulated data stays at 5. Do not raise the gate settings below to clear a particular row; use Prerequisites signed off instead.
Setting | Value | What it does
Weight: Value | 1 | Relative weight in the score. Equal weights by default; e.g. set 2 to count value double.
Weight: Data sensitivity | 1 | Relative weight in the score.
Weight: Effort | 1 | Relative weight in the score.
Weight: Risk | 1 | Relative weight in the score.
Weight: Readiness | 1 | Relative weight in the score.
Gate: data sensitivity at or above | 5 | Rows at or above this are 'Prerequisites first'.
Gate: risk at or above | 5 | Rows at or above this are 'Prerequisites first'.
Gate: readiness at or below | 1 | Rows at or below this are 'Prerequisites first'.
Do first: score at or above | 70 | Ungated rows at or above this score are 'Do first'.
Next: score at or above | 50 | Ungated rows from this score up to the Do first threshold are 'Next'; below are 'Later'.
Source of the idea: NIST AI RMF Playbook (https://airc.nist.gov/airmf-resources/playbook/), MAP 1.5 suggested actions: establish risk tolerance levels and identify a maximum allowable risk tolerance above which the system will not be deployed. NIST does not prescribe these numbers.

## NIST mapping
Worksheet column | NIST AI RMF 1.0 outcome it gives evidence for | Outcome text (NIST AI 100-1)
Candidate use case; Data it needs | MAP 1.1 | Intended purposes, potentially beneficial uses, context-specific laws, norms and expectations, and prospective settings in which the AI system will be deployed are understood and documented.
Value | MAP 1.4; MAP 3.1 | MAP 1.4: The business value or context of business use has been clearly defined or - in the case of assessing existing AI systems - re-evaluated. MAP 3.1: Potential benefits of intended AI system functionality and performance are examined and documented.
Data sensitivity; Risk | MAP 3.2 | Potential costs, including non-monetary costs, which result from expected or realized AI errors or system functionality and trustworthiness - as connected to organizational risk tolerance - are examined and documented.
Effort; Score; Rank (by analogy: MANAGE 1.2 is about treating risks, not choosing projects) | MANAGE 1.2 | Treatment of documented AI risks is prioritized based on impact, likelihood, and available resources or methods.
Gated? and Prerequisites signed off (Scales tab gate; modelled on the Playbook's MAP 1.5 suggested action) | MAP 1.5 | Organizational risk tolerances are determined and documented.
Readiness: named owner; policy covers this use | GOVERN 1.3 | Processes, procedures, and practices are in place to determine the needed level of risk management activities based on the organization's risk tolerance.
Readiness: baseline measured; Next step (pilot) | MANAGE 1.1 | A determination is made as to whether the AI system achieves its intended purposes and stated objectives and whether its development or deployment should proceed.
Sources
NIST AI 100-1, AI RMF 1.0 | https://nvlpubs.nist.gov/nistpubs/ai/NIST.AI.100-1.pdf
NIST AI RMF Playbook | https://airc.nist.gov/airmf-resources/playbook/
NIST AI 600-1, Generative AI Profile | https://nvlpubs.nist.gov/nistpubs/ai/NIST.AI.600-1.pdf
The mapping is CIO Support guidance. Subcategory numbers are from AI RMF 1.0, which NIST says is being revised.

## Lists
1-5 | Yes/No
1 | Yes
2 | No
3
4
5