## How to use
Microsoft 365 Copilot readiness checklist
Copilot only shows people content they can already open, so most of this checklist is about permissions. It has 30 items in seven areas. We suggest working through areas 1 and 2 first, then 3 to 6 before you widen licensing beyond the pilot.
Checklist tab: set Status for each item (Done, In progress, Not started, Not applicable), name an owner, note where the evidence is, and set a target date. Items marked Not started turn red. The Summary tab counts statuses per area automatically. The Source column links the Microsoft Learn page each item comes from.
Site review tab: one row per SharePoint site you are reviewing, for example https://contoso.sharepoint.com/sites/Finance. Record the owner (leave it blank if the site has none: those are the riskiest), whether it holds sensitive content, the oversharing found, the access review dates, and any temporary protection or label applied. 'Ready for Copilot' is your decision; set it to Yes only when the owner has completed the review and the status is Fixed and verified. A Yes without both turns amber. For a site holding CUI, PHI or GxP records, also record sign-off from the person who owns that obligation (compliance, privacy or quality) before you set Yes.
Licensing notes reflect Microsoft Learn pages last updated between December 2025 and October 2026, checked on October 19, 2026. Microsoft changes Copilot features, names and licensing often: check the linked pages before you buy or rely on a feature.
Text marked 'CIO Support suggestion' is our advice. The rest restates Microsoft's published guidance.
If you handle controlled unclassified information (DFARS/CMMC), protected health information (HIPAA) or GxP records, decide before you assign licenses whether Copilot should reach that content at all. Confirm with your compliance officer, privacy officer or quality unit which Microsoft cloud, contract terms (such as a HIPAA business associate agreement) and validation steps apply. Tidy permissions do not make Copilot use with that content compliant, and this checklist does not show that you meet those obligations.
Explanation and all sources: cio.support/ai/microsoft-365-copilot-readiness-checklist/
CIO Support by LAN Service Group · cio.support
Free to copy, edit and use inside your organization. General guidance based on Microsoft's public documentation, not legal advice; not published or endorsed by Microsoft.

## Checklist
# | Area | Checklist item | Why it matters | Where in Microsoft 365 | Licensing note | Status | Owner | Evidence (where) | Target date | Notes | Source (Microsoft Learn)
1 | 1. Licensing and prerequisites | Confirm an eligible Microsoft 365 base plan and Copilot licenses for the pilot group, and whether the Purview and SharePoint Advanced Management features you plan to use are covered. | Copilot is included in Microsoft 365 E7 and sold as an add-on to other plans; Microsoft says some readiness features may need more licenses. | Microsoft 365 admin center > Billing > Licenses | Foundational Purview capabilities are in Microsoft 365 E3; optimized features are in E5 or E7. | Not started |  |  |  |  | https://learn.microsoft.com/en-us/microsoft-365/copilot/microsoft-365-copilot-setup
2 | 1. Licensing and prerequisites | Move Copilot users' Microsoft 365 Apps off Semi-Annual Enterprise Channel (Microsoft recommends Current or Monthly Enterprise Channel), and check Microsoft's Copilot network requirements. | Microsoft says Copilot is available in all update channels except Semi-Annual Enterprise Channel. | Microsoft 365 Apps admin center or your device management tool |  | Not started |  |  |  |  | https://learn.microsoft.com/en-us/microsoft-365/copilot/microsoft-365-copilot-setup
3 | 1. Licensing and prerequisites | Decide whether to allow pay-as-you-go agents that use organizational content, and finish the oversharing work first if you do. | Microsoft says users without the Copilot add-on can use pay-as-you-go agents that have access to organizational content. | Microsoft 365 admin center > Copilot | Pay-as-you-go billing. | Not started |  |  |  |  | https://learn.microsoft.com/en-us/microsoft-365/copilot/microsoft-365-copilot-overview
4 | 1. Licensing and prerequisites | Name a rollout owner, set up a test environment and choose a pilot group from several business groups. | Microsoft recommends a test environment, a pilot with a select group and a communication plan. | Microsoft 365 admin center usage reports (to find active users) |  | Not started |  |  |  |  | https://learn.microsoft.com/en-us/microsoft-365/copilot/microsoft-365-copilot-setup
5 | 2. Identity | Enforce multifactor authentication for all users. | Microsoft lists MFA for all users as a Copilot security measure. | Microsoft 365 admin center; Microsoft Entra admin center |  | Not started |  |  |  |  | https://learn.microsoft.com/en-us/microsoft-365/copilot/microsoft-365-copilot-setup
6 | 2. Identity | Review conditional access policies. | Microsoft's readiness checklist asks you to review conditional access. | Microsoft Entra admin center > Conditional Access |  | Not started |  |  |  |  | https://learn.microsoft.com/en-us/microsoft-365/copilot/microsoft-365-copilot-setup
7 | 2. Identity | Review guest and external access; remove guests who no longer need it. | Microsoft says permissions you give to people outside your organization count too. The review itself is a CIO Support suggestion. | Microsoft Entra admin center > Users; SharePoint sharing settings |  | Not started |  |  |  |  | https://learn.microsoft.com/en-us/microsoft-365/copilot/microsoft-365-copilot-privacy
8 | 2. Identity | Disable departed users promptly and review membership of groups that grant access to sensitive sites. | CIO Support suggestion: a group with the wrong members gives the wrong people access to every site the group can open. | Microsoft Entra admin center; Entra access reviews if licensed | Entra access reviews need Microsoft Entra ID Governance or Microsoft Entra Suite; some capabilities work with Entra ID P2. | Not started |  |  |  |  | https://learn.microsoft.com/en-us/entra/id-governance/access-reviews-overview
9 | 3. Find oversharing | Export the top 100 most-used sites from the SharePoint admin center. | Microsoft's setup guide starts the oversharing assessment here. | SharePoint admin center > Active sites |  | Not started |  |  |  |  | https://learn.microsoft.com/en-us/microsoft-365/copilot/microsoft-365-copilot-setup
10 | 3. Find oversharing | Run the 'Site permissions across your organization' snapshot report. | Shows sites with the broadest access, such as thousands of users, guests or 'Everyone except external users'. Microsoft suggests running it quarterly. | SharePoint admin center > Reports > Data access governance | SharePoint Advanced Management, available once at least one user has a Copilot license. | Not started |  |  |  |  | https://learn.microsoft.com/en-us/sharepoint/data-access-governance-reports
11 | 3. Find oversharing | Review the Purview DSPM for AI data risk assessment for your top sites. | Microsoft says DSPM for AI runs a weekly data risk assessment for the top 100 SharePoint sites by usage. | Microsoft Purview portal > DSPM for AI | Check your Purview licensing. | Not started |  |  |  |  | https://learn.microsoft.com/en-us/purview/dspm-for-ai
12 | 3. Find oversharing | Run the sharing links and 'Shared with Everyone except external users' activity reports. | Shows where oversharing happened in the last 28 days. Microsoft suggests running them monthly. | SharePoint admin center > Reports > Data access governance |  | Not started |  |  |  |  | https://learn.microsoft.com/en-us/sharepoint/data-access-governance-reports
13 | 3. Find oversharing | Run the content management assessment to find sites with oversized audiences, broken inheritance or no owner, and inactive sites. | Ownerless sites have nobody to fix them; Microsoft says cleaning up inactive content also improves Copilot answer quality. | SharePoint admin center (SharePoint Advanced Management) | SharePoint Advanced Management. | Not started |  |  |  |  | https://learn.microsoft.com/en-us/microsoft-365/copilot/configure-secure-governed-data-foundation-microsoft-365-copilot
14 | 4. Fix oversharing | Disable 'Everyone except external users' at tenant level and restrict company-wide sharing groups and Anyone links. | Stops new oversharing being created while you clean up the old. Existing grants are removed site by site in item 17 (CIO Support suggestion). | SharePoint admin center or SharePoint Online PowerShell (see the Microsoft Learn setup guide) |  | Not started |  |  |  |  | https://learn.microsoft.com/en-us/microsoft-365/copilot/configure-secure-governed-data-foundation-microsoft-365-copilot
15 | 4. Fix oversharing | Confirm every site to be reviewed has a current owner (site ownership policy). | Site access reviews go to site owners, who must be available to respond. | SharePoint admin center (SharePoint Advanced Management) | SharePoint Advanced Management. | Not started |  |  |  |  | https://learn.microsoft.com/en-us/sharepoint/site-access-review
16 | 4. Fix oversharing | Start site access reviews for overshared sites from the data access governance reports. | Site owners know who should have access. Up to 100 sites at once from the report, more with PowerShell. SharePoint sites only, not OneDrive. | SharePoint admin center > Reports > Data access governance > Initiate site access review | SharePoint Advanced Management. | Not started |  |  |  |  | https://learn.microsoft.com/en-us/sharepoint/site-access-review
17 | 4. Fix oversharing | Site owners remove excess users, groups and company-wide links (including 'Everyone except external users'), rescope sharing links and fix broken permission inheritance. | This is the actual fix; reports and reviews only point to it. | Site permissions and Manage access in SharePoint |  | Not started |  |  |  |  | https://learn.microsoft.com/en-us/microsoft-365/copilot/configure-secure-governed-data-foundation-microsoft-365-copilot
18 | 4. Fix oversharing | Plan OneDrive clean-up separately (sharing links and broad access in OneDrive). | CIO Support suggestion: site access review does not support OneDrive, so OneDrive needs its own plan. | SharePoint admin center reports; OneDrive sharing settings |  | Not started |  |  |  |  | https://learn.microsoft.com/en-us/sharepoint/site-access-review
19 | 5. Temporary protections | Apply Restricted Content Discovery to high-risk SharePoint sites while they are reviewed. | Limits the site's content in organization-wide search and Copilot responses. It does not change permissions, Copilot can still work on a document a user already has open, and Microsoft describes it as temporary. | SharePoint admin center > Active sites, or PowerShell | Requires a Copilot license; SharePoint sites only. | Not started |  |  |  |  | https://learn.microsoft.com/en-us/sharepoint/restricted-content-discovery
20 | 5. Temporary protections | Apply restricted access control to business-critical sites (for example finance, HR or legal: CIO Support suggestion). | Only members of up to 10 named groups who also have permission can open the site; Copilot and search honor it. Shared and private channel sites need their own policy. | SharePoint admin center > Policies > Access control | SharePoint Advanced Management. | Not started |  |  |  |  | https://learn.microsoft.com/en-us/sharepoint/restricted-access-control
21 | 5. Temporary protections | Remove interim protections once access and permissions are fixed. | Microsoft's guidance; Microsoft also cautions that overusing Restricted Content Discovery reduces what Copilot can draw on. | SharePoint admin center |  | Not started |  |  |  |  | https://learn.microsoft.com/en-us/microsoft-365/copilot/configure-secure-governed-data-foundation-microsoft-365-copilot
22 | 6. Sensitivity labels and DLP | Enable sensitivity labels for Office files in SharePoint and OneDrive, and publish your label set (a short set to start: CIO Support suggestion). | Until enabled, SharePoint and OneDrive cannot process files encrypted with a label, so search, eDiscovery, DLP and co-authoring do not work for them. Files already encrypted must be edited or uploaded again. | Microsoft Purview portal > Information Protection |  | Not started |  |  |  |  | https://learn.microsoft.com/en-us/purview/sensitivity-labels-sharepoint-onedrive-files
23 | 6. Sensitivity labels and DLP | Use labels that apply encryption without the EXTRACT usage right for content Copilot must not summarize. | With VIEW but not EXTRACT, Copilot will not summarize it for other users. The person who applied the encryption keeps EXTRACT, and Copilot in Edge can reference it from an open tab unless DLP is used in Edge. A label without encryption does not stop Copilot. | Microsoft Purview portal > Information Protection > Labels |  | Not started |  |  |  |  | https://learn.microsoft.com/en-us/purview/ai-m365-copilot-considerations
24 | 6. Sensitivity labels and DLP | Decide whether to add a Purview DLP for Copilot policy for labeled files, emails or sensitive prompts. | Microsoft's guidance uses DLP for Copilot to exclude sensitive content from Copilot grounding. | Microsoft Purview portal > Data loss prevention | Check the Purview service description for which plan includes it. | Not started |  |  |  |  | https://learn.microsoft.com/en-us/microsoft-365/copilot/configure-secure-governed-data-foundation-microsoft-365-copilot
25 | 6. Sensitivity labels and DLP | Do not rely on site or team labels to label the files inside them. | Container labels (Teams, groups, sites) are not inherited by the items inside them. | Microsoft Purview; SharePoint site settings |  | Not started |  |  |  |  | https://learn.microsoft.com/en-us/purview/ai-m365-copilot-considerations
26 | 6. Sensitivity labels and DLP | Check label coverage, then add default labels, auto-labeling and required site labels for new sites. | Microsoft's guardrail step after remediation. | SharePoint data access governance > Sensitivity label report; Purview | Microsoft lists the sensitivity label report as needing E5 or G5. | Not started |  |  |  |  | https://learn.microsoft.com/en-us/sharepoint/sharepoint-advanced-management-features-copilot-license
27 | 7. Audit, pilot and operate | Confirm unified audit logging is on and audit-log retention is set to your compliance needs. | Copilot interactions are logged in Audit (Standard), with references to the files and sites used. | Microsoft Purview portal > Audit |  | Not started |  |  |  |  | https://learn.microsoft.com/en-us/purview/audit-copilot
28 | 7. Audit, pilot and operate | Decide how long to keep Copilot interactions, or when to delete them, and confirm eDiscovery can find them. | Microsoft's step for regulatory requirements. Setting retention for Copilot interactions does not by itself meet any specific regulation or records-retention obligation. | Microsoft Purview > Data Lifecycle Management; eDiscovery |  | Not started |  |  |  |  | https://learn.microsoft.com/en-us/microsoft-365/copilot/configure-secure-governed-data-foundation-microsoft-365-copilot
29 | 7. Audit, pilot and operate | Pilot with users whose sites are already reviewed; test prompts that would expose a problem and check the audit log. | Microsoft says to check through Purview auditing and reports that Copilot no longer surfaces restricted content. The test prompts are a CIO Support suggestion. | Microsoft Purview > Audit; DSPM Activity explorer |  | Not started |  |  |  |  | https://learn.microsoft.com/en-us/microsoft-365/copilot/configure-secure-governed-data-foundation-microsoft-365-copilot
30 | 7. Audit, pilot and operate | Widen licensing in waves; re-run permission snapshot reports quarterly and activity reports monthly. | Microsoft's pilot, deploy and operate phases, and its suggested report cadence. | Microsoft 365 admin center Copilot reports; SharePoint data access governance |  | Not started |  |  |  |  | https://learn.microsoft.com/en-us/sharepoint/data-access-governance-reports

## Site review
Site URL or name | Site owner | Holds sensitive content? | Broad access found (EEEU, large groups, guests) | Anyone or company-wide links found? | Broken inheritance? | Access review sent (date) | Owner completed (date) | Restricted Content Discovery applied? | Restricted access control applied? | Sensitivity label | Status | Ready for Copilot? | Notes

## Summary
Area | Items | Done | In progress | Not started | Not applicable | Blank
1. Licensing and prerequisites | 4
2. Identity | 4
3. Find oversharing | 5
4. Fix oversharing | 5
5. Temporary protections | 3
6. Sensitivity labels and DLP | 5
7. Audit, pilot and operate | 4
Total
Sites listed for review
Sites with no owner
Sites marked ready for Copilot
Ready = Yes without a completed, verified fix
CIO Support suggestion: there is no pass mark. Widen Copilot licensing beyond the pilot only when areas 3 to 6 are done for the sites the next group of users can reach.

## Lists
Status | Yes/No | Site status
Done | Yes | Not started
In progress | No | Review sent
Not started | Unknown | Owner completed
Not applicable |  | Fixed and verified
Archived or deleted